## Vulnerabilities
Vuln ID | Task | Title | Severity | CWE | Status | Description | Remediation Applied / Recommended
SEC-001 | P1-1 | Default Fallback JWT Secret in Production | Medium | CWE-1188 | Fixed & Verified | Settings silently defaulted to 'dev-secret-change-in-prod' in production. | Added @model_validator(mode='after') in Settings raising ValueError if production/staging uses default secret.
SEC-002 | P1-1 | Potential Sensitive Data Leakage in Log Extras | Medium | CWE-532 | Fixed & Verified | JSONFormatter copied uninspected extra fields into log entries, risking secret exposure. | Implemented is_sensitive_key() with pattern matching, automatically masking sensitive attributes with '***REDACTED***'.
SEC-003 | P1-1 | Permissive CORS Parsing Risk | Low | CWE-942 | Identified (Guarded) | Unsanitized comma-separated CORS input could allow wildcard '*' with credentials. | CORS middleware explicit allow_origins configuration from settings; disallow wildcard credentials.
SEC-004 | P1-1 | Unpinned Third-Party GitHub Actions Tags | Low / Info | CWE-829 | Accepted Risk | Workflows used @v4 and @v3 tags instead of immutable commit SHAs. | For enterprise production, pin GitHub Action steps to full commit SHAs.
SEC-101 | P1-2 | Header Injection / HTTP Response Splitting Defense | Low | CWE-113 | Fixed & Verified | Incoming X-Request-ID reflected in response header could allow CRLF response splitting. | Added SAFE_REQUEST_ID_REGEX (^[a-zA-Z0-9_-]{1,128}$) validating and discarding unapproved characters.
SEC-102 | P1-2 | Health Probe Reconnaissance / Version Disclosure | Low / Info | CWE-200 | Identified | GET /health reveals API version string '0.1.0' to unauthenticated callers. | In production environment, consider suppressing detailed build metadata on public endpoints.
SEC-103 | P1-2 | Readiness Probe Resource Exhaustion (DoS) | Low | CWE-400 | Protected | Heavy network queries during frequent probe calls can cause service degradation. | Implemented probe_readiness() with in-memory non-blocking configuration validation with 0 I/O overhead.
SEC-201 | P1-3 | Test JWT Token Replay / Cross-Environment Guard | Low | CWE-347 | Protected | Test tokens signed with static test key could be replayed against non-test instances if secrets matched. | Production runtime enforces unique production JWT secret via Pydantic model validator, rendering test tokens invalid.
SEC-202 | P1-3 | Ephemeral Database and Checkpoint Isolation | Low | CWE-212 | Protected | Test suites writing to persistent SQLite files risk leaking sensitive test fixtures onto disk. | conftest.py enforces in-memory SQLite and checkpoints (:memory:) guaranteeing zero residual disk state.
SEC-301 | P1-4 | Environment Secret Exposure Verification in Template | Low | CWE-200 | Protected | Template files checked into source control risk leaking developer secrets or live API keys. | Verified .env.example contains safe placeholders only; automated test_no_committed_env_file gates CI.
SEC-302 | P1-4 | Makefile Shell Injection and Parameter Safety | Low | CWE-78 | Protected | Makefile recipes running external commands could suffer command injection if unquoted variables were used. | POSIX-compliant parameter expansion with safe fallback defaults (${BASE_URL:-http://localhost:8000}).
SEC-401 | P2-1 | SQL Injection Mitigation via Declarative Mapped Types | High | CWE-89 | Protected | Improperly sanitized user inputs in SQL statements could allow SQL injection. | SQLAlchemy 2.0 type-annotated mapped_column with parameterized queries and strict input typing.
SEC-402 | P2-1 | Relational Cascade Integrity and Audit Immutability | Medium | CWE-404 | Protected | Cascading deletes could inadvertently purge security audit logs or leave orphaned child records. | Configured ondelete=CASCADE on transient children and isolated AuditLog without foreign key cascade, guaranteeing immutable audit trails.
SEC-501 | P2-2 | Service Role Key Isolation and RLS Anon Containment | High | CWE-285 | Protected | Service role key could be leaked to client bundles or anon role granted unintended table access. | Strict client key isolation (anon key only on client) and RLS denies anon access across all tables except published articles.
SEC-502 | P2-2 | Trigger Function Search Path Manipulation | Low | CWE-426 | Protected | Functions executing without schema qualification could suffer search_path hijack. | set_updated_at plpgsql function explicitly references NOW() and operates safely within trigger scope.
SEC-601 | P2-3 | Database Connection String and Credential Sanitization | Medium | CWE-209 | Protected | Database connection URLs with embedded credentials could be exposed in debug logs or uncaught exception traces. | Database engine configured with echo=False; JSON logging formatter automatically masks sensitive fields (password, secret, token, key).
SEC-602 | P2-3 | Parameterized ORM Filtering and Attribute Access Control | High | CWE-89 | Protected | Dynamic filter values or malicious search strings could lead to SQL injection or unauthorized attribute access. | Repository queries strictly utilize SQLAlchemy 2.0 type-safe expressions with parameterized query generation; verified via SQL injection test.
SEC-701 | P2-4 | Sample Dataset Secret and PII Exposure Prevention | Medium | CWE-312 | Protected | Sample datasets or SQL seed scripts could accidentally bundle real production API keys, secrets, or customer PII. | All demo entities utilize synthetic profiles with RFC 2606 reserved domains (.test, .demo); verified by automated regex secret scanning test.
SEC-702 | P2-4 | Production Data Pollution via Demo Bootstrap Execution | Medium | CWE-284 | Protected | Automated demo seed execution could contaminate live production database tables if run outside demo environment. | Bootstrap service is strictly guarded behind DEMO_MODE=true in lifespan and implements database emptiness checks to prevent accidental execution.